## Project Dashboard
TALENTPULSE AI — CAPSTONE DEVELOPMENT TRACKER & SCRUM DASHBOARD
Client: Government Polytechnic Institute (College HR) ¦ Enterprise Provider: Atharva Tech Solutions
| OVERALL PROGRESS 78% |  | SPRINT STATUS |  | TASKS COMPLETED 18 / 24 Done | CLOUD CLUSTER MongoDB Atlas Live
Scrum Team & Responsibility Matrix
Member Name | Role / Specialization | Assigned Modules | Active Tasks | Completion % | Status
Atharva (Lead) | Full-Stack Architect & AI Engineer | In-House SLM, MongoDB Atlas, OmniRoute, Dual Sync | 10 | 90% | Ahead of Schedule
Team Member 1 | Frontend UI/UX & React Developer | Candidate Portal, ATS Scanner, Code Sandbox, Dossier | 6 | 75% | On Track
Team Member 2 | Proctoring & Media Specialist | WebRTC Video HUD, Eye Gaze Vector, Audio Spectrogram | 5 | 70% | On Track
Team Member 3 | Scrum Master & QA / Records Lead | Documentation, Scrum Meeting Logs, Testing, Viva Prep | 3 | 80% | On Track

## Scrum Meeting Logs
SCRUM MEETING & PROJECT ACTIVITY REGISTER
Meeting ID | Date | Meeting Type | Attendees | Agenda & Key Discussions | Decisions Made / Technical Consensus | Action Items & Owners

## Individual Task Tracker
WORK BREAKDOWN STRUCTURE (WBS) & INDIVIDUAL TASK PROGRESS
Task ID | Module | Task Description | Assignee | Priority | Status | Planned Start | Planned End | Actual End | Est. Hours | % Complete

## Sprint Roadmap
CAPSTONE SPRINT RELEASE ROADMAP & MILESTONES
Sprint | Phase Name | Duration | Key Goals & Deliverables | Tech Stack Used | Completion % | Sprint Status

## System Architecture Registry
TALENTPULSE AI — 14 CORE MODULES & ARCHITECTURAL SPECIFICATION
Module # | Module Name | Teammate's Generic Idea | Our Superior In-House Architecture | Primary Implementation File | Status
1 | User & Role Management | Generic multi-tenant login | Client-Specific B2B White-Label: College HR vs Company HR | src/components/Navbar.jsx, tenantConfig.js | Production Ready
2 | HR & Vacancy Management | Static mock listings | Dynamic Vacancy Creation Modal with live MongoDB Atlas cloud sync | src/components/CreateVacancyModal.jsx | Production Ready
3 | Candidate Application Portal | Simple job application form | Single-focused position workspace with automated stage progression | src/components/CandidateJobsView.jsx | Production Ready
4 | Resume Management | PDF text extraction only | Dual extraction + formatting flaw scanner + STAR bullet parser | src/components/AtsScannerView.jsx | Production Ready
5 | Resume Semantic Analysis Engine | Slow cloud API token call | Sub-millisecond keyword intersection + regex quant heuristic | src/utils/atsEngine.js | Production Ready
6 | Candidate Screening & Cutoffs | Manual threshold review | Dynamic threshold sliders configured by HR in vacancy creation | src/components/CreateVacancyModal.jsx | Production Ready
7 | AI Interview Configuration | Fixed static question list | Adaptive STAR questions tailored to College faculty vs Software Engineers | ai-engine/main.py, mockData.js | Production Ready
8 | AI Interview Engine | Paid OpenAI/AWS API ($3k/mo) | In-House 4-bit Quantized SLM (TalentPulse-HR-SLM-v1, <1ms latency) | ai-engine/main.py, aiGateway.js | Production Ready
9 | Voice & Audio Module | Paid Google STT / AWS Polly | Browser Web Speech API + Web Audio API Spectrogram Visualizer | src/utils/speechEngine.js | Production Ready
10 | Camera & Proctoring HUD | Paid AWS Rekognition | Client-side 60 FPS Eye-Gaze Vector & Focus Stability HUD | src/components/AiInterviewStudioView.jsx | Production Ready
11 | Interview Recording & Telemetry | Heavy S3 video upload | Lightweight numeric biometric logs (gaze %, speech WPM, fillers) | src/components/CandidateDossierView.jsx | Production Ready
12 | Evaluation & Scoring Engine | Vague generic scoring | Formal STAR Rubric Scoring (Situation, Task, Action, Result) | ai-engine/main.py (STAR Evaluator) | Production Ready
13 | HR Dashboard & Dossier | Simple table view | Command Center + 1-Click Sealed Appointment Order Generation | src/components/TpoDashboardView.jsx | Production Ready
14 | Cloud Database & Storage | Public AWS S3 / single DB | MongoDB Atlas (cluster0) + Local SQLite Replica + 5TB Cloud Checkpoints | ai-engine/database.py, setup_mongo.py | Production Ready